X PLATFORM

Web Application Implementation Plan

Engineering Team — Project Blueprint

Version 1.0  •  Confidential

1. Executive Summary

X Platform is a full-featured, web-based scheduling and session management system designed to connect students with instructors across multiple organizations. The platform handles the complete lifecycle of a learning engagement — from instructor onboarding and availability management, to student booking, live session delivery, and post-session analytics.

This document serves as the master implementation plan for the engineering team, covering architecture, user roles, feature modules, data models, integrations, phased delivery, and task breakdown.

Next.js + Node.js + PostgreSQL

Tech Stack

4 User Roles

Platform Admin / Org Admin / Instructor / Student

5 Phase Delivery

MVP → Analytics → Integrations → Mobile → Optimize

~9–12 Months

Estimated Build Timeline

2. User Roles & Permissions

The platform defines four distinct user roles, each with specific permissions and views. Role-based access control (RBAC) will be enforced at both the API and UI layers.

2.1 Platform Admin (Super Admin)

The highest privilege level. Has full read/write access across all organizations.

•	Manage all organizations, instructors, students, and admins

•	Define the global subject/topic taxonomy

•	Assign instructors to organizations and students to instructors

•	Access all analytics, reports, and exports

•	Configure platform-wide settings (cancellation policies, notification templates)

•	Broadcast announcements to all users

2.2 Organization Admin (Org Admin)

Manages a specific organization and its members. Can belong to multiple organizations.

•	Manage instructors and students within their org

•	Assign students to instructors within their org

•	Set availability on behalf of instructors

•	View org-scoped reports and analytics

•	Configure org-level settings

2.3 Instructor

Teaching staff who can belong to multiple organizations simultaneously.

•	Manage personal profile and subject specialties

•	Set recurring weekly availability and manual time slots

•	Sync calendar with Google Calendar / Outlook

•	View upcoming and past sessions

•	Share files and resources with students

•	Access in-session tools (video, whiteboard, chat)

2.4 Student

Learners who are assigned a pool of instructors by an admin.

•	Book 1-on-1 or group sessions with assigned instructors

•	View available time slots

•	Cancel sessions (within policy window)

•	View session history and upcoming events

•	Access shared files from instructors

•	Receive notifications via Email, SMS, Line, and in-app

3. System Architecture

3.1 Technology Stack

Layer

Technology / Decision

Frontend

Next.js 14+ (App Router), React, TypeScript, Tailwind CSS

Backend / API

Node.js with Express or Next.js API Routes, REST + WebSockets

Database

PostgreSQL (primary), Redis (caching & session store)

ORM

Prisma ORM for schema management and type-safe queries

Authentication

NextAuth.js — Email/Password + Google SSO + Microsoft SSO

File Storage

AWS S3 or equivalent (recordings, shared files)

Real-time

Socket.io for in-app notifications and chat

Queue / Jobs

Bull + Redis for async jobs (notifications, reminders)

i18n

next-intl — English + Traditional Chinese (zh-TW)

Deployment

Vercel (frontend) + Railway/Render or AWS (backend)

CI/CD

GitHub Actions — lint, test, build, deploy pipeline

3.2 High-Level Architecture

The system follows a layered architecture separating concerns cleanly:

•	Presentation Layer: Next.js SSR/CSR with role-based routing and layout guards

•	API Layer: RESTful endpoints with JWT auth middleware and RBAC guards

•	Service Layer: Business logic (booking rules, availability conflicts, notifications)

•	Data Layer: PostgreSQL via Prisma, Redis for caching hot data (available slots)

•	Integration Layer: External calendar sync, video conferencing, messaging services

•	Job Layer: Bull queues for email/SMS/Line dispatch, reminder scheduling

4. Core Data Model

Below are the primary database entities and their key relationships. Full schema DDL will be generated by the engineering team using Prisma migrations.

4.1 Key Entities

Entity

Key Fields

Relationships

User

id, email, name, role, locale, avatar, phone, line_id

belongs to many Orgs, has many Sessions

Organization

id, name, slug, settings, timezone

has many Users (via OrgMembership)

OrgMembership

user_id, org_id, role (admin/instructor/student)

links User to Organization

Subject

id, name_en, name_zh, category, is_active

managed by Platform Admin

InstructorProfile

user_id, bio, subjects[], rating, org_ids[]

extends User for instructors

Availability

id, instructor_id, type (recurring/manual), day, start_time, end_time

belongs to Instructor

CalendarSync

id, user_id, provider, access_token, refresh_token, last_synced

belongs to User

StudentInstructor

student_id, instructor_id, org_id, assigned_by

admin-managed assignment

Session

id, type (1on1/group), subject_id, instructor_id, start_time, end_time, status, meeting_url

core booking entity

SessionParticipant

session_id, user_id, role, status (confirmed/cancelled)

links Users to Sessions

Notification

id, user_id, type, channel, payload, sent_at, read_at

all notification records

FileResource

id, session_id, uploaded_by, url, filename, size

shared session files

Recording

id, session_id, url, duration, created_at

session recordings

5. Feature Modules

5.1 Authentication & Onboarding

•	Email/password registration with email verification

•	SSO via Google OAuth 2.0 and Microsoft Azure AD

•	JWT-based sessions with refresh token rotation

•	Role-based onboarding flow (different first-run UX per role)

•	Profile setup wizard: name, avatar, timezone, preferred language (EN/ZH-TW)

•	Password reset via email

5.2 Organization Management

•	Platform Admin: Create / edit / deactivate organizations

•	Org Admin: Invite users (instructors/students) via email link

•	Instructor can belong to multiple orgs simultaneously

•	Org-scoped settings: timezone, cancellation window, branding

•	Org Admin dashboard: member directory, activity summary

5.3 Instructor Profile & Subject Management

•	Instructor profile: bio, photo, subjects, languages, rating (display)

•	Subject assignment: instructors select from platform admin's subject list

•	Subjects have EN and ZH-TW names, categories, and active/inactive flags

•	Platform Admin manages the global subject taxonomy

•	Student-facing instructor cards show subjects, availability indicator, rating

5.4 Availability Management

•	Recurring weekly schedule: set available hours per weekday

•	Manual slot creation: open specific date/time windows

•	Admin override: Org Admin can manage availability on instructor's behalf

•	External calendar sync: Google Calendar and Outlook (OAuth-based)

•	Conflict detection: prevent double-booking across orgs

•	Buffer time settings: optional gap between sessions

•	Timezone handling: all times stored in UTC, displayed in user's local timezone

5.5 Booking System

•	Student views available slots for their assigned instructors only

•	1-on-1 booking: select instructor → subject → date/time → confirm

•	Group session booking: instructor creates group event, students join

•	Booking confirmation triggers multi-channel notification

•	Cancellation enforced by configurable X-hour policy (e.g. 24hrs)

•	Waitlist support for group sessions at capacity

•	Rescheduling: cancel + rebook flow (within cancellation policy)

•	Calendar invite auto-sent on booking (Google/Outlook .ics)

5.6 Session & Event Management

•	Upcoming sessions dashboard for all roles

•	Past sessions history with status (completed / cancelled / no-show)

•	Session detail view: participants, subject, notes, files, recording

•	Instructor can add session notes post-session

•	Admin can view all sessions across org

5.7 In-Session Features

•	Video conferencing: deep-link or iframe integration with Zoom / Google Meet / Microsoft Teams

•	In-platform chat: real-time messaging between session participants (Socket.io)

•	File sharing: upload/download resources within a session context

•	Whiteboard: integration with Excalidraw (open-source) or Miro embed

•	Session recording: captured via video conferencing provider, stored in S3

•	Playback: students and instructors can review recordings post-session

5.8 Notifications & Messaging

•	In-app notification bell: real-time via Socket.io

•	Email: transactional emails via SendGrid or AWS SES

•	SMS: via Twilio or similar provider

•	Line Messaging App: via Line Messaging API (requires Line Business account)

•	Calendar invites: .ics file attached to booking confirmation email

•	Google Calendar / Outlook: auto-create event via calendar API on booking

Notification triggers:

•	Booking confirmed (to student + instructor)

•	Session cancelled (to all participants)

•	Session reminder: 24hrs before + 1hr before

•	Admin announcement broadcast

5.9 Admin Dashboard & Analytics

•	Platform-level: total users, orgs, sessions, active instructors

•	Org-level: sessions per period, instructor utilization, student activity

•	Instructor performance: sessions completed, ratings, cancellation rate

•	Student progress: sessions attended, subjects covered, attendance rate

•	Subject analytics: most-booked subjects, trend over time

•	Export: CSV / Excel download for all major report types

•	Report module designed as extensible — new report types can be added without core changes

6. Third-Party Integrations

Service

Provider

Purpose

Priority

Video

Zoom / Google Meet / Teams

Session delivery via meeting URL

P0

Calendar

Google Calendar API

Sync availability + create events

P0

Calendar

Microsoft Graph API (Outlook)

Sync availability + create events

P0

Email

SendGrid or AWS SES

Transactional email notifications

P0

SMS

Twilio

SMS notifications & reminders

P1

Messaging

Line Messaging API

Line push notifications

P1

File Storage

AWS S3 / Cloudflare R2

Files, recordings, avatars

P0

Whiteboard

Excalidraw (self-hosted) / Miro

Collaborative whiteboard

P2

Auth SSO

Google OAuth 2.0

Single Sign-On

P0

Auth SSO

Microsoft Azure AD

Single Sign-On

P0

P0 = Required for MVP  |  P1 = Phase 2  |  P2 = Phase 3

7. Phased Delivery Plan

The project is divided into 5 phases. Each phase builds on the previous and can be demonstrated to stakeholders independently.

Phase 1  ·  Months 1–3

Foundation & MVP

Goal: Working end-to-end booking flow. Stakeholders can create orgs, onboard instructors, assign students, and book sessions.

•	Project setup: monorepo, CI/CD, environments (dev/staging/prod)

•	Database schema + Prisma migrations (all core entities)

•	Authentication: Email/password, Google SSO, Microsoft SSO

•	User management: roles, profiles, onboarding flow

•	Organization CRUD and membership management

•	Subject taxonomy (Platform Admin)

•	Instructor availability: recurring weekly + manual slots

•	Student-Instructor assignment (admin-managed)

•	Booking flow: 1-on-1 session booking + cancellation

•	Session dashboard: upcoming + past events (all roles)

•	Email notifications: booking confirmation, cancellation, reminders

•	Basic admin dashboard: user counts, session list

•	i18n setup: EN + ZH-TW strings for all MVP screens

•	Mobile-responsive layout for all MVP pages

Phase 2  ·  Months 4–5

Scheduling & Integrations

Goal: Full scheduling power, calendar sync, group sessions, and additional notification channels.

•	Google Calendar & Outlook sync (availability + event creation)

•	Calendar invite (.ics) on booking confirmation

•	Group session creation and student join/cancel

•	Waitlist for full group sessions

•	In-app real-time notifications (Socket.io)

•	SMS notifications via Twilio

•	Line Messaging API integration

•	Admin override: set availability on behalf of instructors

•	Conflict detection and buffer time settings

•	Timezone-aware UI for all date/time displays

Phase 3  ·  Months 6–7

In-Session Features

Goal: Rich in-session experience including video, chat, file sharing, whiteboard, and recordings.

•	Video conferencing deep-link integration (Zoom / Meet / Teams)

•	In-platform real-time chat (per session)

•	File upload/download within session context (S3)

•	Session recording storage and playback

•	Whiteboard integration (Excalidraw embed)

•	Post-session notes by instructor

•	File resource library per instructor/student

Phase 4  ·  Months 8–9

Analytics & Reporting

Goal: Admin analytics dashboards, performance reports, subject analytics, and CSV/Excel exports.

•	Platform-level analytics dashboard

•	Org-level usage and activity reports

•	Instructor performance reports (sessions, ratings, cancellations)

•	Student progress tracking (attendance, subjects covered)

•	Subject activity analytics and trends

•	CSV and Excel export for all major report types

•	Extensible report framework for future additions

Phase 5  ·  Months 10–12

Hardening & Optimization

Goal: Production-readiness — performance, security, accessibility, and polish.

•	Performance optimization: caching, query tuning, CDN configuration

•	Security audit: OWASP top 10, penetration testing

•	Accessibility audit: WCAG 2.1 AA compliance

•	Load testing and horizontal scaling strategy

•	Comprehensive end-to-end test suite (Playwright)

•	Monitoring and alerting setup (Datadog or Sentry)

•	Full ZH-TW translation review with native speaker

•	User acceptance testing (UAT) with pilot group

•	Documentation: API docs, admin guide, user guide

8. Engineering Task Breakdown

Each task is estimated in story points (SP) using Fibonacci scale: 1=trivial, 2=small, 3=medium, 5=large, 8=very large, 13=epic (should be broken down).

8.1 Infrastructure & DevOps

Task ID

Task

Description

Est. SP

INF-01

Monorepo setup

Turborepo with apps/web, apps/api, packages/db, packages/ui

3

INF-02

CI/CD pipeline

GitHub Actions: lint, type-check, test, build, deploy to staging

5

INF-03

Environment config

Dev / staging / prod env vars, secrets management

2

INF-04

Database provisioning

PostgreSQL + Redis setup, connection pooling (PgBouncer)

3

INF-05

Prisma schema init

All core entities, indexes, migrations pipeline

5

INF-06

S3 bucket setup

Buckets for avatars, files, recordings. IAM roles.

2

INF-07

Monitoring setup

Sentry error tracking, uptime monitoring

3

INF-08

Seed data scripts

Dev seed: orgs, instructors, students, subjects

2

8.2 Authentication

Task ID

Task

Description

Est. SP

AUTH-01

NextAuth.js setup

Base config, session strategy, JWT setup

3

AUTH-02

Email/password auth

Registration, login, email verification flow

5

AUTH-03

Google SSO

Google OAuth 2.0 provider integration

3

AUTH-04

Microsoft SSO

Azure AD OIDC integration

3

AUTH-05

Password reset

Forgot password email flow with secure token

3

AUTH-06

RBAC middleware

Role-based route guards for API + Next.js pages

5

AUTH-07

Onboarding wizard

Post-login profile setup per role

5

AUTH-08

Session refresh

Refresh token rotation, logout everywhere

3

8.3 User & Organization Management

Task ID

Task

Description

Est. SP

USR-01

User profile CRUD

Edit name, avatar, phone, locale, timezone

3

USR-02

Instructor profile

Bio, subjects, availability preview

3

USR-03

Org CRUD (platform admin)

Create, edit, deactivate organizations

3

USR-04

Invite flow

Email invite link → registration → role assignment

5

USR-05

Multi-org membership

Instructor belongs to multiple orgs, context switcher

5

USR-06

Student-Instructor assignment

Admin assigns pool of instructors to student

3

USR-07

Subject taxonomy

Platform admin CRUD for subjects, EN+ZH-TW

3

USR-08

Member directory

Org admin view of all members + search/filter

3

8.4 Availability & Scheduling

Task ID

Task

Description

Est. SP

SCH-01

Recurring availability UI

Weekly schedule grid (Mon–Sun, time blocks)

5

SCH-02

Manual slot creation

Add/remove specific date-time slots

3

SCH-03

Admin override

Org admin edits instructor availability

3

SCH-04

Google Calendar sync

OAuth2 + Calendar API to read/write events

8

SCH-05

Outlook calendar sync

Microsoft Graph API for calendar integration

8

SCH-06

Conflict detection

Prevent double-bookings across orgs + calendars

5

SCH-07

Timezone engine

UTC storage, per-user display conversion (date-fns-tz)

3

SCH-08

Buffer time settings

Configurable gap between consecutive sessions

2

SCH-09

Available slots API

Compute + cache open slots for student booking view

5

8.5 Booking & Session Management

Task ID

Task

Description

Est. SP

BKG-01

1-on-1 booking flow

Select instructor → subject → slot → confirm

5

BKG-02

Group session create

Instructor/admin creates group event with capacity

5

BKG-03

Group session join

Student joins group session, capacity enforced

3

BKG-04

Cancellation flow

X-hour policy check, confirmation, status update

5

BKG-05

Waitlist

Queue students for full group sessions, auto-notify

5

BKG-06

Session dashboard

Upcoming + past sessions view for all roles

5

BKG-07

Session detail page

Full session info, participants, status, actions

3

BKG-08

Admin session view

All sessions across org with filters/search

3

BKG-09

Post-session notes

Instructor adds notes after session completes

2

8.6 Notifications

Task ID

Task

Description

Est. SP

NTF-01

Bull queue setup

Redis-backed job queue for async notification dispatch

3

NTF-02

Email notifications

SendGrid/SES templates: booking, cancel, reminder

5

NTF-03

In-app notifications

Socket.io real-time bell notifications

5

NTF-04

SMS notifications

Twilio integration, message templates

3

NTF-05

Line Messaging API

Line Business setup, push message templates

5

NTF-06

Calendar invites

.ics generation + email attachment on booking

3

NTF-07

Calendar API events

Auto-create Google/Outlook event on booking confirm

5

NTF-08

Reminder scheduler

Cron jobs: 24hr + 1hr before session reminders

3

NTF-09

Admin broadcast

Platform/org admin sends announcement to user groups

3

NTF-10

Notification preferences

User can toggle channels per notification type

3

8.7 In-Session Features

Task ID

Task

Description

Est. SP

SES-01

Video meeting link

Generate/store Zoom / Meet / Teams link per session

3

SES-02

In-platform chat

Real-time chat per session (Socket.io + persistence)

8

SES-03

File upload

Upload files to session, stored in S3, listed in UI

5

SES-04

File download

Download shared files, access control per session role

2

SES-05

Whiteboard embed

Excalidraw iframe with session-scoped rooms

5

SES-06

Recording storage

Webhook from video provider → store recording in S3

5

SES-07

Recording playback

Video player page with access control

3

8.8 Analytics & Reporting

Task ID

Task

Description

Est. SP

RPT-01

Platform admin dashboard

KPI cards: users, orgs, sessions, active rates

5

RPT-02

Org analytics dashboard

Org-scoped: session volume, instructor utilization

5

RPT-03

Instructor performance

Sessions, cancellation rate, subjects taught

5

RPT-04

Student progress

Attendance rate, subjects, session history

5

RPT-05

Subject analytics

Booking trends per subject, most popular, heatmap

5

RPT-06

CSV export

Export sessions, users, subjects to CSV

3

RPT-07

Excel export

Formatted XLSX reports with multiple sheets

5

RPT-08

Report framework

Pluggable report module for future custom reports

5

8.9 Internationalization (i18n)

Task ID

Task

Description

Est. SP

I18N-01

next-intl setup

Routing, locale detection, message files (en / zh-TW)

3

I18N-02

EN translations

All UI strings in English message files

5

I18N-03

ZH-TW translations

Traditional Chinese translation of all UI strings

8

I18N-04

Date/time formatting

Locale-aware date, time, relative formatting

2

I18N-05

Language switcher

User preference saved to profile, persists across sessions

2

I18N-06

Native speaker review

ZH-TW copy reviewed and corrected by native speaker

3

9. Open Questions & Decisions Required

The following items require decisions from stakeholders before engineering can proceed:

#

Question

Why It Matters

1

Which video conferencing provider is preferred — Zoom, Google Meet, or Teams? Or all three?

Each has different API integration complexity. Zoom is most standard for EdTech.

2

What is the exact cancellation window (X hours)?

Drives the cancellation policy enforcement logic in the booking service.

3

Will instructors have a personal rating/review system?

Impacts the InstructorProfile schema and student-facing UI.

4

Should students be able to message instructors outside of sessions?

Determines scope of the chat system (session-only vs. DMs).

5

Is there a payment/billing module planned?

If yes, this is a significant addition that needs its own phase.

6

Are recordings stored indefinitely or purged after X days?

Drives S3 storage costs and retention policy configuration.

7

Will the whiteboard be Excalidraw (open source) or a paid tool like Miro?

Affects licensing cost and integration approach.

8

How should the Line Messaging API user ID be collected from users?

Line IDs require a specific opt-in/linking flow via Line Login.

9

Are there any PDPA / GDPR data privacy obligations?

Taiwan PDPA applies if handling personal data of Taiwan residents.

10

What is the expected scale at launch (users, orgs, sessions/day)?

Informs infrastructure sizing and caching strategy.

10. Risks & Mitigations

Risk

Severity

Mitigation

Calendar sync API rate limits (Google/Outlook)

High

Implement caching + exponential backoff; store tokens securely with refresh logic

Line Messaging API requires Business verification

Medium

Start Line Business account application early; plan 2-4 week approval lead time

Multi-timezone scheduling edge cases

High

Store all times in UTC; use battle-tested date-fns-tz; extensive QA with multiple timezones

Double-booking across orgs for same instructor

High

Database-level locking on slot reservation; conflict detection before confirmation

ZH-TW translation quality

Medium

Engage native Taiwanese Mandarin speaker for review in Phase 5

Scope creep on analytics module

Medium

Cap Phase 4 to defined reports; design extensible framework for additions post-launch

Video provider API changes / pricing

Low

Abstract video integration behind a provider interface for easy swap

11. Recommended Next Steps

•	Resolve all Open Questions (Section 9) in a stakeholder meeting — target within 1 week

•	Finalize team composition: how many frontend, backend, fullstack engineers + designer?

•	Set up project management tooling (Linear, Jira, or Notion) and import task list from Section 8

•	Begin Phase 1 sprint planning: assign tasks, set sprint length (recommended: 2-week sprints)

•	Initiate Line Business account application and video conferencing provider decision immediately (longest lead times)

•	Schedule design kickoff: wireframes for booking flow, availability management, and dashboards

•	Establish weekly engineering sync and bi-weekly stakeholder demo cadence

X Platform Implementation Plan  •  Version 1.0  •  Prepared for Engineering Team